| Activity Time (months) | Preceding activity | Description | Activity |
| --- | --- | --- | --- |
| 1 | None | Define Requirements | A |
| 3 | A | Design Hardware | B |
| 4 | B | Build and Test Hardware | C |
| 4 | A | Code Software | D |
| 4 | D | Test Software | E |
| 2 | E,C | Integrate System | F |